## Planeador de Projetos
Micro OLED Screen Expansion
[5 empty] | Relevant Period: | 1
Work Packages | Planned Start | Planned Duration | Real Start | Real Duration | Conclusion Percentage | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6
Study NASA Guidelines | 1 | 1 | 1 |  | 0%
Develop Communication Protocols | 2 | 1 |  |  | 0%
Develop Split-Screen Algorithm | 2 | 2 |  |  | 0%
Develop Memory Test Protocols | 2 | 2 |  |  | 0%
Develop System Maintenance Protocols | 3 | 1 |  |  | 0%
PCB Design | 4 | 1 |  |  | 0%
PCB Compliance Testing | 5 | 1 |  |  | 0%
PCB Production | 5 | 1 |  |  | 0%
PCB Physical Testing | 5 | 1 |  |  | 0%