## Planeador de Projetos
Micro OLED Screen Expansion
[6 empty] | Relevant Period: | 1
Work Areas | Work Packages | Planned Start | Planned Duration | Real Start | Real Duration | Conclusion Percentage | Days (December)
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Study NASA Guidelines | 1 | 20 |  |  | 0%
Communication protocol | SPI | 3 | 10 | 3 | 3 | 100%
| I2C | 3 | 10 | 3 | 3 | 100%
Screen library | Screen communication Library | 13 | 2 | 6 | 2 | 50%
Split Screen algorithm | Develop Split-Screen Algorithm | 13 | 2 |  |  | 0%
Memory Test Protocols | Flash Test | 15 | 4 |  |  | 0%
| Ram test | 15 | 4 |  |  | 0%
| Eeprom test | 15 | 4 | 10 |  | 0%
PCB Design | PCB Design | 17 | 2 |  |  | 0%